## Incident Log
Date | Site | Severity | Category | Description
2026-04-01 | Store 1 | High | Paperwork | Variation order unsigned at dispatch
2026-04-02 | Store 2 | Medium | Scheduling | Shutdown window changed after labor was booked
2026-04-03 | Store 3 | High | Vendor | Commissioning engineer unavailable
2026-04-04 | Store 2 | Low | Comms | Updated contact list not circulated
2026-04-05 | Store 1 | High | Scheduling | Install date slipped by five days
2026-04-06 | Store 3 | Medium | Paperwork | Drawing revision emailed but not logged

## Request
Create a new sheet named Executive Summary.
Add three short summary bullets based on the incident log.
The bullets should capture dominant operational themes, not copy raw rows verbatim.