## Weekly Plan
Workstream | Lead | Mon | Tue | Wed | Thu | Fri | Dependencies | Risk Notes
Data migration | J. Hu | schema freeze | dry run 1 | issue triage | vendor sync | signoff | Legacy export + VPN approval | Text overflows because the risk note is intentionally verbose and column I is too narrow.
Dashboard QA | M. Cole | filter test | chart review | label fixes | UAT prep | stakeholder readout | Updated mockups from design | Two reviewers are using older screenshots, so defect comments may be stale.
Finance pack | R. Malik | collect inputs | variance draft | revise wording | controller review | publish | Late regional commentary | The row height is too short for wrapped content and clips the last line.
Cutover comms | A. Lim | draft email | legal check | translate | final approval | send | Brand review window | One hidden fragility is that the table currently spills beyond a portrait print width.
This sheet is intentionally awkward to print cleanly.