## Slide 1
3. Implementation Plan
Install window, shutdown sequencing, and handover steps.

## Slide 2
1. Executive Summary
Overall delay, commercial impact, and immediate decision needed.

## Slide 3
4. Appendix
Reference notes, contacts, and spare observations.

## Slide 4
2. Root Cause
Paperwork delay, unclear shutdown ownership, and vendor gaps.