3. Appendix Materials

Reference acronyms, supplier abbreviations, and archived maintenance notes.

1. Executive Summary

The refrigeration retrofit is delayed by five days and needs one immediate go/no-go decision.

4. Next Steps

Confirm install window, approve variation order, and send corrected shutdown calendar.

2. Findings

Vendor paperwork gaps and ownership confusion caused the current delay.