## Program Plan
Program Plan
Item | Owner | Start | End
1. Mobilization | PMO | Jun 1 | Jun 3
Permit packet review | Ravi | Jun 1 | Jun 2
Vendor kickoff | Maya | Jun 2 | Jun 3
2. Field prep | Ops | Jun 4 | Jun 7
Site walkdown | Elena | Jun 4 | Jun 5
Temporary barriers | Jon | Jun 5 | Jun 7
3. Commissioning | Controls | Jun 8 | Jun 12
Loop checks | Nina | Jun 8 | Jun 10
Punch-list closeout | Maya | Jun 11 | Jun 12