## Slide 1
Implementation Plan
Shift cable-tray recovery to weekend crew.
Lock revised vendor sequence by Tuesday.

## Slide 2
Appendix
Detailed task list.
Site-by-site owner map.

## Slide 3
Root Cause
Vendor lead time extended by two weeks.
Inspection backlog grew after repeat holds.

## Slide 4
Executive Summary
<fill three bullets here>