## Slide 1
Schedule Review
Launch moved to 25 July after cabling slip.
Recovery work is focused on testing and turnover.

## Slide 2
Status Update
Critical: Launch remains on track for 18 July.
Training materials are still in review.
Vendor walkdown is complete.