Project Closeout Draft

Findings

Permit approval is still delayed by one cycle.

Supplier backlog is pushing the valve-kit arrival into the second half of June.

Teams are using a temporary safety workaround to keep inspections moving.

Appendix Materials

Appendix item A: vendor tracker.

Appendix item B: permit correspondence.

Next Steps

Confirm revised permit date with the city reviewer.

Lock the supplier recovery sequence before the next steering update.