Action Tracker

| Owner | Due Date | Action |
| --- | --- | --- |
| Maya Chen | 14 Jun 2026 | Confirm vendor recovery sequence |
| Ravi Shah | 16 Jun 2026 | Issue revised install date note |
| Elena Park | 18 Jun 2026 | Prepare client update deck |

Draft note 1

Vendor is still a bit late, so we might slip by one week if the revised install date does not hold.

Draft note 2

Client update can probably wait until we lock the revised install date from the vendor team.