| Owner | Due Date | Action |
| --- | --- | --- |
| Maya Chen | 14 Jun 2026 | Confirm vendor recovery |
| Ravi Shah | 16 Jun 2026 | Issue install memo |
| Elena Park | 18 Jun 2026 | Prepare client update |

Status notes

Confirm vendor recovery - Status: On track

Issue install memo - Status: Waiting on vendor

Prepare client update - Status: Drafting