## IAP_DRAFT_2026-07-15
DRAFT Field | Working Value | PRIVATE Notes
Incident | City Heat Emergency IAP | mayor backchannel wants softer shelter language
Operational Period | 2026-07-15 0600-1800 | do not release until union review
Vendor liability | Cooling bus contract pending | vendor liability / personal phone 555-0140

## ICS_202_Objectives_PRIVATE
Objective ID | Operational Period | Public Objective | Owner | Status | INTERNAL Note
OBJ-01 | 2026-07-15 0600-1800 | Open six cooling centers before peak heat index | Operations | Active | shelter shortage rumor
OBJ-02 | 2026-07-15 0600-1800 | Complete wellness checks for priority registry residents | Human Services | Active | staffing grievance
OBJ-03 | 2026-07-15 0600-1800 | Maintain transit shuttles to cooling centers every 30 minutes | Transportation | Active | PRIVATE
OBJ-04 | 2026-07-15 0600-1800 | Publish hourly public heat safety updates | Public Information | Active | DRAFT
OBJ-05 | 2026-07-15 0600-1800 | Stage medical support at North Cooling Cneter by 1800 | Medcial | Active | volunteer medical rumor

## ICS_203_Org
Role | Assigned Lead | Agency | Public Contact | Internal Phone
Incident Commander | Daria Chen | Emergency Management | EOC main desk | personal phone 555-1001
Operations Section Chief | Marcos Silva | Fire Department | Operations desk | PRIVATE
Planning Section Chief | Nina Patel | Emergency Management | Planning desk | PRIVATE
Logistics Section Chief | Theo Brooks | Public Works | Logistics desk | PRIVATE
Public Information Officer | Avery Morgan | Mayor's Office | PIO desk | mayor backchannel
Safety Officer | Leah Grant | Health Department | Safety desk | INTERNAL

## ICS_204_Assignments
Branch ID | Branch | Location | Field Teams | Support Staff | Working Total | Objective | Status | Private Note
BR-01 | Cooling Centers | North Cooling Cneter | 9 | 14 | 23 | OBJ-01 | Active | do not release
BR-02 | Wellness Checks | East Senior Registry | 12 | 8 | 20 | OBJ-02 | Active | staffing grievance
BR-03 | Transit Shuttle | Central Depot | 7 | 6 | 13 | OBJ-03 | Active | vendor liability
BR-04 | Public Information | EOC Media Room | 3 | 5 | 8 | OBJ-04 | Active | mayor backchannel
BR-05 | Medcial | North Cooling Cneter | 5 | 7 | 12 | OBJ-05 | Active | volunteer medical rumor
BR-06 | Logistics | Public Works Yard | 6 | 10 | 16 | OBJ-01 | Active | scratch

## ICS_205_Comms
Net | Channel | Frequency | Use | Priority | Contact | PRIVATE Note
Command | CMD-1 | 155.010 | Unified command | Primary | EOC radio desk | INTERNAL
Operations | OPS-3 | 155.220 | Field branches | Primary | Operations desk | INTERNAL
Medical | TAC-6 | 155.460 | Medical staging and triage | Primary | Medical desk | needs correction
Logistics | LOG-2 | 154.980 | Supplies and facility support | Primary | Logistics desk | scratch
Public Information | PIO-1 | 156.110 | Public messaging coordination | Primary | PIO desk | mayor backchannel
Backup | CITY-ALT | 453.700 | Backup voice channel | Backup | EOC radio desk | PRIVATE

## ICS_206_Medical
Medical Asset | Location | Lead | Capacity | Staging Time | PRIVATE Note
EMS Strike Team Alpha | North Cooling Cneter | Rene Walsh | 24 | 1800 | ambulance staging 1800
Mobile Clinic Bravo | East Senior Registry | Mika Torres | 18 | 1700 | volunteer medical rumor
Triage Bus Charlie | Central Depot | Ibrahim Noor | 20 | 1630 | INTERNAL
Behavioral Health Team Delta | EOC Family Assistance | June Park | 12 | 1600 | PRIVATE

## Correction_Log_INTERNAL
Correction ID | Field | Old Value | Corrected Value | Applied | Private Reviewer Note
COR-001 | Location | North Cooling Cneter | North Cooling Center | No | do not release
COR-002 | Assigned Lead | Marcos Silva | Marisol Silva | No | staffing grievance
COR-003 | Branch | Medcial | Medical | No | PRIVATE
COR-004 | Channel | TAC-6 | TAC-7 | No | INTERNAL
COR-005 | Staging Time | ambulance staging 1800 | ambulance staging 1900 | No | volunteer medical rumor

## Style_Reference
Element | Requirement | PRIVATE Implementation Note
Header fill | 7030A0 | approved public IAP purple
Header font | White bold | do not release design note
Body font | Calibri | INTERNAL
Freeze panes | Header row frozen on public tabular sheets | scratch
Autofilter | Enabled on public tabular sheets | PRIVATE

## scratch_vendor
scratch | vendor liability | personal phone
bus contractor | vendor liability unresolved | 555-1888
cooling center supplies | do not release | mayor backchannel

## mayor notes
PRIVATE | mayor backchannel | shelter shortage rumor
note | avoid shortage language | staffing grievance