## Deviation Log
Deviation ID | Study/Area | Issue | Severity | CAPA ID | Public Boundary
D-203 | ONC-412 | Visit window miss trend | Major | CAPA-17 | Publish summary only
D-219 | Records | eTMF upload lag | Major | CAPA-18 | Publish audit-trail summary
D-226 | Supply Chain | Temperature excursion with unblinded lot notes | Closed | CAPA-21 | Internal only
D-241 | Central Lab | Certificate mismatch for screening lab | Critical | CAPA-24 | Publish blocked status

## CAPA Plan
CAPA ID | Owner Alias | Due Date | Evidence IDs | Draft Status | Reviewer Note
CAPA-17 | P. Shah | 2026-08-14 | E-17A; E-17B | Ready | Effectiveness check still at risk
CAPA-18 | M. Cruz | 2026-09-01 | E-18A | Ready | Implemented and verified
CAPA-21 | N. Patel | 2026-07-20 | E-21A | Closed | Retain in workbook, exclude from deck
CAPA-24 | L. Ortiz | 2026-08-05 | E-24A | Pending | Blocked by missing lab certificate