## Timeline
Time | Event | Phase | Severity
09:05 | Alert fired for checkout latency | Detection | S1
09:18 | Payments failover started | Containment | S1
09:42 | Checkout latency returned below threshold | Recovery | S2
10:15 | Comms update published to support | Communication | S2

## Actions
Action ID | Action | Owner | Due Date | Status
IR-21 | Patch retry backoff in payment gateway | Dana Kim | 2026-08-03 | Open
IR-22 | Publish customer-facing incident FAQ | Luis Romero | 2026-08-04 | Watch
IR-23 | Add synthetic checkout monitor | Nora Singh | 2026-08-07 | Open