## Schedule Update
Activity | Baseline Finish | Current Finish | Critical Path Days | Cause
Corridor B ceiling close-in | 2026-05-09 | 2026-05-12 | 3 | Bypass piping reroute
Exterior delivery staging | 2026-05-08 | 2026-05-09 | 0 | Weather delivery delay
Substantial completion | 2026-09-15 | 2026-09-18 | 3 | Critical path resequence