Draft: Board Memo

TOC placeholder - update fields

# Appendix A - Metrics

Draft: Open items: 3

Draft: Closed items: 12

# Executive Summary

Draft: This memo is ready for board circulation.

Draft: The release package is fully prepared.

# Program Snapshot

Draft: All core milestones are on track.

Draft: No open blockers remain for publication.

# Board Actions

Draft: Approve the release plan at the next meeting.

Draft: Confirm the publication date.

# Obsolete Draft Notes

Draft: Remove this scratch section before publication.

Draft: Internal reviewer notes must not remain in the released file.

| Action | Owner | Status |
| --- | --- | --- |
| Draft: Approve release plan | Draft: Board | Draft: Pending |
| Draft: Confirm publication date | Draft: PMO | Draft: Draft |

Reference body style anchor.